## Sheet1
System Name | BookSmith
Members: | Lynnon Lance Antor
Uriel Alexis Parantar
Statuses |  | Todo
In-Progress
Done
On-hold
[5 empty] | August |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  | December
Tasks | Assignee | Date Started | Date Finished | Status | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
1. REGISTRATION
1.1. Creating UI | Lynnon Lance Antor | 2024-09-22 | 2024-09-30
1.2. Front-End Validation | Lynnon Lance Antor | 2024-09-23 | 2024-09-30
1.3. Integrate with db | Lynnon Lance Antor | 2024-09-25 | 2024-09-30
1.4. Handle Form Submission | Lynnon Lance Antor | 2024-09-25 | 2024-09-30
1.5. Redirect and Feedback | Lynnon Lance Antor | 2024-09-23 | 2024-09-30
2. LOG IN
2.1. Creating UI | Lynnon Lance Antor | 2024-09-25 | 2024-09-30
2.2. Front-End Validation | Lynnon Lance Antor | 2024-09-26 | 2024-09-30
2.3. Authenticate User Credentials | Lynnon Lance Antor | 2024-09-26 | 2024-09-30
2.4. Error Handling | Lynnon Lance Antor | 2024-09-26 | 2024-09-30
2.5. Redirect and FeedBack | Lynnon Lance Antor | 2024-09-25 | 2024-09-30
3. LOG OUT
3.1. Create log out button | Uriel Alexis Parantar | 2024-09-30 | 2024-09-30
3.2. Redirect the user | Uriel Alexis Parantar | 2024-09-30 | 2024-09-30
4. LANDING PAGE
4.1. Creating Best Seller UI | Uriel Alexis Parantar | 2024-09-26 | 2024-09-28
4.2 Integrate UI to Database | Uriel Alexis Parantar | 2024-09-28 | 2024-09-28
4.2. Search Functionality | Uriel Alexis Parantar | 2024-09-30 | 2024-10-15
4.2.1. Create Search Bar UI | Uriel Alexis Parantar | 2024-09-30 | 2024-09-30
4.2.2. Back End Search Logic | Uriel Alexis Parantar | 2024-09-30 | 2024-10-15
4.3.3. Search Result Page | Uriel Alexis Parantar | 2024-09-30 | 2024-10-13
4.3.4. Filtering Search Result | Uriel Alexis Parantar | 2024-10-03 | 2024-10-15
4.4. Book Details Page Integration | Uriel Alexis Parantar | 2024-10-03 | 2024-10-15
4.6 Creating Recommended UI | Uriel Alexis Parantar | 2024-09-26 | 2024-09-28
4.7 Creating Featured Product UI | Uriel Alexis Parantar | 2024-09-26 | 2024-09-28
5. BOOK PURCHASING
5.1. Create UI | Lynnon Lance Antor | 2024-10-02 | 2024-10-14
5.2. Shopping Cart Integration | Lynnon Lance Antor | 2024-10-02 | 2024-10-14
5.3. Create Check Out Process | Lynnon Lance Antor | 2024-10-02 | 2024-10-21
5.4. Back End Order Processing | Lynnon Lance Antor | 2024-10-04 | 2024-10-21
5.5 Digital Content Delivery | Uriel Alexis Parantar | 2024-10-04 | 2024-10-25
6. ONLINE BOOK READING
6.1. Back End Content Management | Uriel Alexis Parantar | 2024-10-10 | 2024-10-21
6.2. Basic Reading Interface | Uriel Alexis Parantar | 2024-10-05 | 2024-10-11
6.3. Page Navigation | Uriel Alexis Parantar | 2024-10-05 | 2024-10-09
7. ABOUT US
7.1 Create UI | Lynnon Lance Antor | 2024-09-27 | 2024-09-27
7.2 Front-End Validation | Lynnon Lance Antor | 2024-09-27 | 2024-09-27
73. Vission Statement | Lynnon Lance Antor | 2024-09-27 | 2024-09-27
8. CONTACT US
8.1 Create UI | Lynnon Lance Antor | 2024-09-27 | 2024-09-28
8.2 Handle Form Submission | Lynnon Lance Antor | 2024-09-27 | 2024-09-28
9. UPDATE PROFILE
9.1 Create UI | Uriel Alexis Parantar | 2024-10-10 | 2024-10-13
9.2 Implement Validation | Uriel Alexis Parantar | 2024-10-10 | 2024-10-24
9.3 Handle Password Validation | Uriel Alexis Parantar | 2024-10-10 | 2024-10-24
9.4 Error Handling and Feedback | Uriel Alexis Parantar | 2024-10-10 | 2024-10-24
10. COMMENT FEATURE
10.1 UI Creation | Lynnon Lance Antor | 2024-11-04 | 2024-11-18
10.2 Database Handling | Lynnon Lance Antor | 2024-11-04 | 2024-11-18
10.3 Backend Logic | Lynnon Lance Antor | 2024-11-04 | 2024-11-18
10.4 Frontend and Backend Integration | Lynnon Lance Antor | 2024-11-04 | 2024-11-18
10.5 Testing and Optimization | Lynnon Lance Antor | 2024-11-04 | 2024-11-18
11. WISHLIST FEATURE
11.1 UI Creation | Uriel Alexis Parantar | 2024-11-04 | 2024-11-18
11.2 Database Handling | Uriel Alexis Parantar | 2024-11-04 | 2024-11-18
11.3 Backend Handling | Uriel Alexis Parantar | 2024-11-04 | 2024-11-18
11.4 Front end and Backend Integration | Uriel Alexis Parantar | 2024-11-04 | 2024-11-18
11.5 Testing and Optimization | Uriel Alexis Parantar | 2024-11-04 | 2024-11-18